# CIS 4374 Semester Project - Smart Parking Platform

Vision, Scope, and Software Requirements Specification (SRS)

Project: Smart Parking Platform
Version: 4.0 (Draft)
Date: October 29th, 2026

Contents

CIS 4374 Semester Project - Smart Parking Platform	1

1. Project Research for Existing Software	5

How Will the Smart Parking Application We Are Building Be Different?	6

2. Project Vision and Scope	7

2.1 - Company Introduction	7

2.2 - Project Overview	7

2.3 - Project Acquisition Description	7

2.4 - Scope	8

2.5 - Users	8

3. Overall System Description	9

3.1 - Overall System Description	9

3.2 - Project Management Plan	9

3.3 - Project Constraints	9

3.4 - High Level Project Requirements	9

4. Functional Requirements	9

5. Non-Functional Requirements	10

6. Draft of SRS with Use Cases	11

7. Project Planning	13

7.1 - Work Breakdown Structure (WBS) - Complete Task List	13

7.2 - Project Timeline - Gantt Chart	15

7.3 - Smart Parking Platform Backlog (Jira)	16

7.4 - Smart Parking Sprint 1 Backlog and Plan (Jira)	18

8. Communication Plan	20

8.1 - Meeting Cadence	20

8.2 - Reporting Processes and Methods	21

8.3 - Stakeholder Communication Responsibilities	21

8.4 - Communication Tools	22

9. Risk Management	22

9.1 - Risk Categories	22

9.2 - Risk Register	23

10. Resources and Cost Management Plan	25

10.1 - Roles and Resources	25

Roles Description Table	25

Roles and Resources Planning Tables	25

10.2 - Resources and Cost Plan (Bottom-Up Cost Plan)	26

10.2.1 - Labor Costs	27

10.2.2 - Non-Labor Costs	27

10.2.3 - Base Project Cost	28

10.2.4 - Contingency	28

10.2.5 - Total Estimated Project Cost	28

10.3 - High Level Cost Plan	29

10.4 - Monthly Cashflows	30

10.5 - RACI Matrix	31

10.6 - Resource and Cost Management Assumptions	32

11. Stakeholder Analysis	33

11.1 - Power Interest Grid	33

12. Team Charter	34

12.1 - Team Information	34

12.2 - Team Scope	35

12.3 - Team Goals	35

12.4 - Team Strengths/Skills	35

12.5 - Roles and Responsibilities	35

12.6 - Success Metrics	36

12.7 - Values and Norms	36

12.8 - Communication Plan and Coordination Tools	37

12.9 - Extra Team Details	37

13. Project Charter	38

13.1 - Project Information	39

13.2 - Project Purpose and Business Need	39

13.3 - Project Objectives	39

13.4 - Project Scope	40

13.4.1 - Project In-Scope	40

13.4.2 - Project Out-Of-Scope	40

13.5 - Key Deliverables	41

13.6 - Project Milestones	42

13.7 - Budget Summary	42

13.8 - Key Stakeholders	42

13.9 - Key Assumptions, Limitations, and Risks	43

13.10 - Success Criteria (High Level)	43

13.11 - Project Authorization for Smart Parking Platform Project	43

# 1. Project Research for Existing Software

During the research phase of this project, I saw that were a number of existing software solutions that try to address issues with parking. Existing software solutions like ParkMobile, SpotHero, Passport Parking, and Easy Park. The following table will go into more detail about these existing solutions.

| Existing Parking Platform Software Solutions |  |  |  |
| --- | --- | --- | --- |
| Solution | What The App Does | Strengths | Weaknesses/Limitations |
| ParkMobile | - Parking lookup - Mobile Payments - Parking Availability - Parking Management Tools - Digital Tools | - Large parking network - Large user base - Supports on-demand and reservations in advance - Parking Availability info and tools to manage pricing | - Reservation availability depends heavily on the specific parking facility - Availability feature is not available in every location - Paywall for some features |
| SpotHero | - Parking Lookup - Reservations - Parking Passes - Reservation Modification - Event Parking | - Strong reservation capabilities - Users can modify reservations before they start | - Reservations don’t guarantee a parking space - In & Out privileges can vary by facility - Availability and features can depend on parking partners |
| Passport Parking | - Mobile Payments - Parking Maps - Update Notifications - Reporting Dashboards - Parking Operator Tools - Remote Extensions | - Strong operator capabilities - Combines payments, reporting, enforcement, and customer parking services | - Primary focus is on mobile payment rather than navigation experience, which is more important to the customers - Depends on integration with other parking platforms |
| Easy Park | - Parking Payments - Parking Lookup - Navigation Assistance - Predictive/Probability for getting parking space | - Heavy focus on helping people locate parking - Uses real-time data and probability estimates to direct users to open spots | - Predictions are probabilities rather than guarantees for the availability of specific parking spots |

Key Points: The existing solutions for this use show that this industry already has some apps that have strong capabilities. However, there is room for improvement for each one, which our application could excel in.

## How Will the Smart Parking Application We Are Building Be Different?

After reviewing the existing software solutions for a Smart Parking Platform, it is evident that there is opportunity for differentiation between our application and their applications. The plan for this Smart Parking Platform is going to combine real-time data, parking reservations, navigation, seamless payments, adequate notifications, and more functionality for operator-side functions. Using real-time data for parking spot occupancy can provide more information to customers for more reliable estimates and availability. This application will differentiate itself from these existing solutions by connecting real-time data on availability, reservations, interactive maps, notifications, and more. This platform will directly support this project’s high-level requirements for things like availability, reservation capabilities, payments, navigation, notifications, and administrative tools. The experience on this app will be more unified, seamless, intuitive, and useful for the potential userbase.

# 2. Project Vision and Scope

## 2.1 - Company Introduction

WE ARE $oftware ¢orp is a software development studio that aims to provide seamless solutions to issues customers may have. The company has an unlimited budget and resources that will allow it to get together development teams and the technologies to support their projects. The goal for this project is to develop a project management plan for the creation of a Smart Parking Platform system.

## 2.2 - Project Overview

The proposed Smart Parking Platform is being created to address the issue regarding people spending too much time trying to get parking. There is also a need for parking operators to have more efficient ways to manage occupancy, pricing, and utilization. For this project, there is a huge emphasis on real-time availability, interactive maps, reservations, payments, analytics, receipts, notifications, management tools, and more. The goal is to develop a project management plan for the creation of this system, including requirements gathering, stakeholder management, scheduling, budgeting, management, and team coordination. Even though there is an unlimited budget, there are several constraints like a fixed timeline, third party dependencies, compliance with privacy and similar requirements, and city & ordinance laws. The scope of this project will be updated throughout the semester.

## 2.3 - Project Acquisition Description

This Smart Parking Platform project was acquired by WE ARE $oftware ¢orp through a competitive approval proposal that was initiated by a city transportation department who wants to improve parking availability, improve reservation capabilities, reduce traffic, and to increase the utilization of parking facilities. There was (RFP) Request for Proposal for a web and mobile platform that can provide real-time parking availability, reservations, payments, navigation, and management tools. Because of WE ARE $oftware ¢orp’s technical approaches and project management capabilities, we were selected to develop the solution. The project will be developed with an unlimited budget and resources but must be done within the timeline.

## 2.4 - Scope

In Scope

- User Registration and Authentication

- Parking Querying and Real-Time Availability

- Interactive Parking Map

- Parking Facility Information

- Parking Reservations

- Digital Payment Processing

- Reservation History and Receipts

- Notifications

- Operator Dashboard

- Reporting and Analytics

- Integration of External Systems

- System Integration and Testing

- Web and Mobile Applications

- Access Controls

- CI/CD Pipelines and Automated Testing

- Deployment Support

Out-of-Scope

- Parking Infrastructure

- Deployment of Parking Sensors

- Hardware Deployment

- Parking Enforcement

- Management of Parking Facilities

- Proprietary Mapping or Payment Networks

- Ownership of Parking Facilities

## 2.5 - Users

- Customers, Users, Those in need of Parking Spaces in Public Spaces

- Parking Facility Facilitators

# 3. Overall System Description

## 3.1 - Overall System Description

The application is a software system that helps drivers locate, reserve, and pay for parking spaces for parking garages in real time. The platform will be available through web and mobile applications and will provide parking availability information, navigation help, and management tools for parking operators. The application is going to include a web application and mobile application, reporting dashboards, payments, reservations, notifications, and external 3rd party integrations.

## 3.2 - Project Management Plan

We are creating a project management plan for the creation of this system, including gathering requirements, resource and cost management, managing communication between stakeholders, scheduling the project, budgeting the project, managing the risks that come with the project, and coordinating all the teams involved.

## 3.3 - Project Constraints

- Unlimited theoretical development budget

- Fixed semester timeline

- Dependence on third-party services and APIs

- Compliance with security and privacy requirements, city ordinance & laws

## 3.4 - High Level Project Requirements

- User Registration and Authentication

- Real-Time Parking Space Availability

- Interactive Map Displaying Available Parking Locations

- Parking Reservation Capability

- Digital Payment Processing

- Reservation History and Receipts

- Administrative Dashboard for Parking Operators

- Occupancy Reporting and Analytics

- Notifications

- Integration with External Navigation and Mapping Services

- Simple and Intuitive User Controls and Interfaces

# 4. Functional Requirements

Functional Requirements

- FR1: The system shall allow users to register and log in securely.

- FR2: The system shall display real-time parking availability.

- FR3: The system shall display parking locations using an interactive map.

- FR4: The system shall allow users to search for parking facilities.

- FR5: The system shall allow users to view parking facility details and pricing.

- FR6: The system shall allow users to reserve a parking space.

- FR7: The system shall allow users to make digital payments on the application.

- FR8: The system shall notify users of parking through sending out parking notifications.

- FR9: The system shall allow users to modify parking reservations.

- FR10: The system shall allow users to quit on their parking reservations.

- FR11: The system shall monitor parking occupancy in certain locations.

- FR12: The system should provide navigation assistance to users.

- FR13: The system shall allow users to monitor parking occupancy at a given location.

- FR14: The system shall allow users manage parking facilities.

- FR15: The system shall create or generate occupancy reports and display parking utilization dashboards.

- FR16: The system shall enforce role-based access so operations employees and customers.

- FR17: The system shall create or generate occupancy reports and display data dashboards.

# 5. Non-Functional Requirements

Non-Functional Requirements

- NFR1: The system shall support at least 1,000 concurrent users.

- NFR2: The system shall display updated parking availability within 5 seconds of receiving new occupancy data.

- NFR3: The system shall provide a simple and intuitive interface for viewing and reserving parking spaces

- NFR4: The system shall be available on commonly used web browsers and mobile devices.

- NFR5: The system shall provide reliable access to parking availability, reservations, and payments.

- NFR6: The system shall respond to standard user requests within 3 seconds in normal operating conditions.

- NFR7: The system shall safekeep user account information from unauthorized access and control.

- NFR8: The system shall encrypt sensitive data stored within the system.

- NFR9: The system shall maintain system performance when processing real-time parking availability, occupancy updates, and more.

- NFR10: The system shall be scalable to support increase in users, parking facilities, occupancy data, and reservations.

- NFR11: The system shall target at least 99% service availability during normal operating periods, excluding planned maintenance.

# 6. Draft of SRS with Use Cases

Use Cases

Use Case 1
Title: Register Account
Actor: Customer
Precondition: User does not have an account
Steps: User enters required information and submits registration.
Postcondition: A user account is created.

Use Case 2
Title: Log In
Actor: Customer
Precondition: User has an account
Steps: User enters valid credentials and selects “Log In.”
Postcondition: User is authenticated.

Use Case 3
Title: Find Available Parking
Actor: Customer
Precondition: User has access to the platform
Steps: User enters a destination and views available parking.
Postcondition: Available parking options are displayed.

Use Case 4
Title: View Parking Map
Actor: Customer
Precondition: Parking locations are available
Steps: User opens the map and selects a parking location.
Postcondition: Selected parking facility is displayed.

Use Case 5
Title: View Parking Details
Actor: Customer
Precondition: Parking facility is selected
Steps: User views availability, pricing, and facility information.
Postcondition: Parking information is displayed.

Use Case 6
Title: Reserve Parking Space
Actor: Customer
Precondition: User is logged in and parking is available
Steps: User selects a time and confirms the reservation.
Postcondition: Parking is reserved.

Use Case 7
Title: Make Digital Payment
Actor: Customer
Precondition: User has a reservation
Steps: User selects a payment method and submits payment.
Postcondition: Payment is processed and recorded.

Use Case 8
Title: View Reservation History
Actor: Customer
Precondition: User has reservations
Steps: User opens reservation history and selects a reservation.
Postcondition: Reservation details are displayed.

Use Case 9
Title: Receive Parking Notification
Actor: Customer
Precondition: User has an active reservation
Steps: System detects a relevant event and sends a notification.
Postcondition: User receives the notification.

Use Case 10
Title: Modify Reservation
Actor: Customer
Precondition: User has an eligible reservation
Steps: User changes the reservation details and confirms the change.
Postcondition: Reservation is updated.

Use Case 11
Title: Cancel Reservation
Actor: Customer
Precondition: User has an eligible reservation
Steps: User selects “Cancel” and confirms cancellation.
Postcondition: Reservation is cancelled.

Use Case 12
Title: Get Parking Directions
Actor: Customer
Precondition: Parking facility is selected
Steps: User selects “Get Directions.”
Postcondition: Navigation directions are provided.

Use Case 13
Title: Monitor Parking Occupancy
Actor: Parking Operator
Precondition: Operator is logged in
Steps: Operator opens the dashboard and views occupancy information.
Postcondition: Current occupancy is displayed.

Use Case 14
Title: Manage Parking Facility
Actor: Parking Operator
Precondition: Operator has management privileges
Steps: Operator updates parking availability or rates and saves changes.
Postcondition: Facility information is updated.

Use Case 15
Title: Generate Occupancy Report
Actor: Parking Operator
Precondition: Occupancy data is available
Steps: Operator selects a reporting period and generates a report.
Postcondition: An occupancy report is available for review.

# 7. Project Planning

## 7.1 - Work Breakdown Structure (WBS) - Complete Task List

These images show the high-level overview of the project timeline with the WBS created in Microsoft Project.

## 7.2 - Project Timeline - Gantt Chart

The Gantt chart below sums up the project schedule across five phases and a 73-day total duration.

## 7.3 - Smart Parking Platform Backlog (Jira)

Smart Parking Platform Jira Project

## 7.4 - Smart Parking Sprint 1 Backlog and Plan (Jira)

Sprint 1: Build the initial user-facing platform that let’s user register their account, login, query for parking facilities, and see simple parking information. In other words, deliver a working prototype of the User Account, Parking Querying and Reservation, and similar modules. Includes UI/UX making initial designs and wireframes for the application both on mobile and the web.

Duration: ~3 Weeks (19 days)

| Sprint ID | ID | Task | Assigned To | Status | Story Points |
| --- | --- | --- | --- | --- | --- |
| SPP-9 | LOGIN-01 | User Creating Their Account | Auth Team | Done | 3 |
| SPP-10 | LOGIN-02 | User Logging Into Account | Auth Team | In Review | 3 |
| SPP-11 | LOGIN-03 | User Logging Out of Account | Auth Team | In Review | 2 |
| SPP-12 | LOGIN-04 | User Information Management | Auth Team | In Progress | 3 |
| SPP-13 | UI-USER-01 | User Home (Main) Screen | UX/UI Team | Done | 3 |
| SPP-14 | UI-USER-02 | View Parking Facility Details | UX/UI Team | Done | 3 |
| SPP-18 | UI-USER-04 | Users Viewing Querying Suitable Facilities | UX/UI Team | In Progress | 3 |
| SPP-19 | UI-USER-05 | Users Viewing Parking Locations on Interactive Map | UX/UI Team | In Review | 5 |
| SPP-37 | BE-PRO-02 | Authenticating Users When They Login | Backend Team | To Do | 5 |
| SPP-38 | BE-PRO-03 | Managing Authenticated User Sessions | Backend Team | In Review | 3 |
| SPP-41 | BE-PRO-06 | Processing Real-Time Parking Availability Data | Backend Team | In Review | 5 |
| SPP-70 | SEC-01 | Implement User Authentication | SecOps Team | In Review | 3 |
| SPP-71 | SEC-02 | Implement Role-Based Access | SecOps Team | To Do | 5 |
| SPP-79 | UD-01 | Parking Querying and Availability Interface | UX/UI Team | To Do | 5 |
| SPP-80 | UD-02 | Reservation and Payment Interface Design | UX/UI Team | To Do | 5 |
| SPP-81 | UD-03 | Dashboard Prototype Design | UX/UI Team | To Do | 5 |
| SPP-82 | UD-04 | Interface Elements Design on Supported Devices | UX/UI Team | To Do | 3 |
| SPP-83 | UD-05 | Wireframes and Interface Specifications | UX/UI Team | To Do | 5 |

# 8. Communication Plan

The following communication plan will establish how the development teams, project leadership, and stakeholders will communicate progress, share updates, report issues, and coordinate work with each other.

## 8.1 - Meeting Cadence

| Meeting Type | Frequency | Participants | Purpose/Goals |
| --- | --- | --- | --- |
| Daily Stand Up (Async) | Daily by 10:00 AM | Dev Team, Scrum Master | Each member posts what they’ve done in Teams/Slack, what is planned for today, and whatever blockers they may have. |
| Weekly Stand Up (SCRUM, Synchronous) | Weekly | Project Manager, Scrum Master, Representative from Each Dev Team | Review the progress of the current sprint, review risks/blockers, and plan for the upcoming week. Meeting notes should be stored in shared project repository. |
| Weekly Stakeholder Check-In | Weekly | Project Manager, Stakeholders, Product Owner, Relevant Team Representatives | Present a sprint demo to stakeholders and provide project status update. Record feedback and add relevant items to Product Backlog. |
| Sprint Planning | Beginning of Each Sprint | Product | Establish the goals for the next sprint, select backlog items to be worked on, estimate effort using story points, and assign responsibilities. |
| Sprint Retrospective | Conclusion of Each Sprint | Scrum Team | Internally discuss what went well, what the team could improve on, and make adjustments for the next sprint. |
| Sprint Review | Conclusion of Each Sprint | Project Manager, Scrum Team, Product Owner, Stakeholders | Display completed functionality, collect feedback, and review progress toward the project’s goals. |

Project Communication Note: The daily stand up is asynchronous, so team members don’t need to join a meeting. They just need to post their updates by 10 AM each day. However, if the scrum master feels that there needs to be video calls, they can do so. The main channels of communication will be through Microsoft Teams and Slack.

## 8.2 - Reporting Processes and Methods

| Reporting Method | Frequency | Information Communicated | Escalation Path |
| --- | --- | --- | --- |
| Jira | Continuously | Tracks backlog, sprint progress, task ownership, and whatever blockers. | Team Scrum Master |
| Project Report Status | Weekly | Report milestones, schedule, progress, and the risks. | Project Manager |
| Microsoft Project | Weekly | Update WBS, Gantt Chart, dependencies, and milestone changes. | Project Manager |
| Slack | Daily / As Needed | Share daily stand-ups, questions, and whatever blockers. | Scrum Master Project Manager |
| Microsoft Teams | Scheduled Meetings / As Needed | Hold video meetings, sprint prototypes, and stakeholder check-ins. | Project Manager |
| Shared Project Repository | Update Continuously | Store meeting minutes, decisions, documentation, and status reports for cross-team access and viewing. | Project Manager |

Escalation Rules: Whatever issues can push back sprint commitments, project milestones, and sensitive information should be reported immediately rather than waiting until the next team meeting.

Escalation Path: Team Member  Team Lead  Scrum Master  Project Manager

## 8.3 - Stakeholder Communication Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Maintain the project schedule, status reports, and stakeholder communication. Facilitate team meetings, ensure sprint deliverables are delivered on time, and communicate updates and prototypes to stakeholders. |
| Product Owner | Communicate requirements for the product, emphasize the importance of the Backlog, and specify and clarify user needs. |
| Scrum Master | Facilitate Scrum events, coordinate communication with Dev Team, and help resolve blockers. |
| Development Team Leads | Report team progress, technical issues, be engaged with team, and coordinate with cross-team collaboration/dependencies. |
| Team Members | Post daily stand ups, attend meetings, complete deliverables, keep up with Jira, and flag blockers. |

Project Documentation Note: Use Jira as the main source of truth for backlog and sprint matters, Microsoft Project for the overall schedule.

## 8.4 - Communication Tools

| Tool | Usage |
| --- | --- |
| Slack | Communication channels for daily asynchronous stand-up updates, quick questions, and questioning potential blockers. |
| Microsoft Teams | Video meetings, weekly team meetings, stakeholder check-ins, screensharing for sprint prototyping, and another channel of communication between project members. |
| Jira | Product Backlog, Sprint Planning, Task Assignments, and Progress Updates. |
| Microsoft Project | WBS, Gantt Chart, project schedule, and milestone progress. |
| Shared Project Repository | Meeting minutes, project documentation, decision-making, technical updates, and status reports. |
| Email | Channel of communication when forwarding messages to entire teams. |

# 9. Risk Management

## 9.1 - Risk Categories

Technical Risks |

- TR1: Third Party Mapping/Navigation  3rd Party mapping or navigation APIs may become unavailable, which could limit the user’s ability to navigate to parking facilities or receive instructions to them.

- TR2: Inaccurate Real-Time Parking Data  Real-time parking data could be delayed or inaccurate, which could lead to users trying to reserve spacings that are no available at that point in time.

- TR3: Application Integration Issues  The web, mobile, and background modules could have integration issues, which could cause certain features to not work across platforms, which could then cause user downtime.

- TR4: Insufficient Payment Gateway Integration  The payment gateway integration may not process transactions correctly, meaning payments could not go through and records could be off.

- TR5: Scalability Issues  The app could face scalability issues if thousands of users are using it simultaneously, especially with all the features and API integrations that are being used in it.

- TR6: Deployment Issues  The app could have issues with deployment or the CI/CD pipelines, which could delay version updates and rollouts.

Schedule Risks |

- SR1: Tasks Take Longer Than Expected  Development tasks may take longer than initially estimated which could delay sprint goals and project milestones.

- SR2: Scope Creep  Changes to requirements may broaden the scope which could put additional work on the team that will make the project exceed the initial timeline.

- SR3: Delayed Stakeholder Feedback  If the stakeholders don’t review deliverables in a timely manner, it could hold the team back from moving on, delaying overall project progress.

- SR4: Third Party API Access and Approval  If the 3rd Party API access and approval is delayed, then project progress might be delayed due to the need for testing the APIs within the application as well as the integration of those APIs.

Financial Risks |

- FNR1: Third-Party Mapping Service Fees  Some 3rd Party and Location services might incur usage fees, which could contribute to large operation expenses, especially as usage builds up.

- FNR2: Large Payment Transaction Fees  Payment gateway providers could charge expensive transactions fees, which could hike up the cost of processing parking payments.

- FNR3: Infrastructure Costs  The technical resources needed to host, run, and serve the application could introduce large infrastructure operating costs, especially if they exceed initial estimates (Cloud hosting, database usage, servers, etc.).

- FNR4: Additional Testing or Development Resources  \The project could require more funding and resources than initially expected, especially if there needs to be new hardware or software purchases.

Note: While the company may have an unlimited theoretical development budget, it is still important to consider financial implications regarding this project.

People Risks |

- PR1: Lack of Communication  Development teams not being on the same page, which could lead to components and modules being incompatible with one another and very distinct interfaces.

- PR2: Team Member Drops Out  Team members could drop out or not be available for their own reasons which could delay the completion of development tasks, especially if they owned important path tasks.

- PR3: Unclear Task Ownership  Unclear task ownership could result in incomplete or duplicated work which slows down sprint progress, commitments, and the completion of deliverables.

- PR4: Lack of Experience with Certain Technologies  Team members could lack experience with certain technologies or lack the competencies for certain tasks, which could lead to the need for additional training and even implementation errors which could delay sprint progress.

## 9.2 - Risk Register

Legend:
TR = Technical Risk
SR = Schedule Risk
FNR = Financial Risk
PR = People Risk

| ID | Description | Probability | Impact | Owner | Response Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- |
| TR3 | Application Integration Issues | High | Very High | Backend/API Team | Conduct integration testing throughout development. | In-Progress |
| TR2 | Inaccurate Real-Time Parking Data | Medium | Very High | Backend/API Team | Validate parking pace data and implement timely availability updates. | In-Progress |
| TR1 | Third Party Mapping/Navigation Issues | High | Very High | Mapping Team | Identify mapping options and test API access in timely manner. | In-Progress |
| SR4 | Issues with Third Party API Access and Approval | Medium | High | Integration Team | Request access to APIs in timely manner and use mock services or made-up data in the meantime. | In-Progress |
| SR2 | Scope Creep | Medium | Medium | Product Owner | Consult with Product Owner to review scope and make changes in Backlog. | In-Progress |
| SR1 | Tasks Take Longer Than Expected | High | Medium | Scrum Master and Team | Review progress during daily stand-up and keep Sprint backlog up to date. Ensure key deliverables are being worked on. | In-Progress |
| PR1 | Lack of Communication | Medium | High | Scrum Master and Teams | Hold regular coordination meetings outside of and during scrum and keep shared documentation up to date. | In-Progress |
| PR4 | Lack of Experience with Certain Technologies | Medium | Low | Technical Leads | Provide technical knowledge, knowledge sessions, and workshops to help team get used to certain technologies. | In-Progress |
| FNR3 | High Infrastructure Costs | High | Medium | Backend/API Team | Monitor resource consumption and configure resource utilization notifications. Confirm that the application workflows, resources, and processes are properly optimized. | In-Progress |
| FNR1 | High Third-Party Mapping Service Fees | Low | Low | Project Manager | Monitor API usage and review provider pricing and usage limits. Compare and contrast with other possible providers that have the same service(s). | In-Progress |
| TR6 | Deployment Issues | Medium | High | DevOps/CI/CD Team | Run pipeline checks in advance and very often, maintain environment configurations, protect secrets, document rollback steps, and maintain manual rollback procedure(s). | In-Progress |

# 10. Resources and Cost Management Plan

## 10.1 - Roles and Resources

### Roles Description Table

The following table details the team members and teams that have been assigned to the Smart Parking Platform application. This details the roles within the project.

| Role / Team | Primary Responsibilities |
| --- | --- |
| Project Manager | Schedule, budget, risk management, stakeholder communication, and project coordination. |
| Product Owner | Product requirements, backlog importance ranking, and stakeholder needs. |
| Scrum Master | Scrum events, team coordination, blockers, process improvement. |
| Technical Lead / Lead Architect | Architecture, technical decisions, and cross-team technical collaboration and dependencies. |
| Mobile Application Team | Mobile application development |
| Web Application Team | Web application development |
| Backend/API Team | Backend services, API integration, database, authentication, and business logic. |
| Mapping / Services Team | Mapping, geolocation, parking locations, navigation functionality. |
| Payment Integration Team | Payment processing and payment service integration. |
| QA and Testing Team | Functionality, integration, performance, reliability, and system testing. |
| SecOps Specialist | Authentication, authorization, privacy, confidentiality, SecOps testing. |
| DevOps / CI/CD Team | Build and test automation, CI/CD Pipelines, environment configuration, deployment and rollback support, pipeline monitoring, and deployment credentials. |
| UI/UX Team | Wireframes, prototypes, user interfaces, accessibility, and usability |

### Roles and Resources Planning Tables

The following HR Plan Table details the team members and teams that have been assigned to the Smart Parking Platform application. The Smart Parking Platform will use a Scrum-Based structure of project leadership, technical leadership, developments teams, 3rd party integration teams, SecOps resources, DevOps resources, and UI/UX resources that collaborate with the development teams. Every name in this project is fictitious.

| Role / Team | Name | Skill Level | FTE% | Hours / Month | Hourly Rate | Monthly Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | Mitch Carter | Senior | 50% (0.50) | 80 | $65 | $5,200 |
| Product Owner | Sarah Davis | Senior | 40% (0.40) | 64 | $60 | $3,840 |
| Backend/API Team | Ryan Patel | Senior | 100% (1.00) | 160 | $65 | $10,400 |
| Technical Lead / Lead Architect | Alex Kipp | Senior | 75% (0.75) | 120 | $75 | $9,000 |
| Mobile Application Team | Noah Goff | Intermediate | 100% (1.00) | 160 | $55 | $8,800 |
| Web Application Team | Ava Davis | Intermediate | 100% (1.00) | 160 | $55 | $8,800 |
| Scrum Master | Greg Brooks | Senior | 45% (0.45) | 72 | $55 | $3,960 |
| Mapping / Services Team | Jordan Chang | Senior | 100% (1.00) | 160 | $63 | $10,080 |
| Payment Integration Team | Ethan Myers | Senior | 100% (1.00) | 160 | $65 | $10,400 |
| SecOps Specialist | Jared Poe | Senior | 50% (0.50) | 80 | $70 | $5,600 |
| QA and Testing Team | Sophia Ramirez | Senior | 100% (1.00) | 160 | $70 | $11,200 |
| DevOps / CI/CD Team | Darius White | Senior | 35% (0.35) | 56 | $80 | $4,480 |
| UI/UX Team | Pam Lee | Intermediate | 35% (0.35) | 56 | $50 | $2,800 |
| Totals | 13 Resources |  |  | 1,488 | $94,560 |  |

Important Assumptions: 100% FTE is equivalent to 160 working hours per month. The percentages represent the portion of each resource’s available working time going towards this project. The hourly payments are market estimates for software professionals.

Total Estimated Hours (Monthly) | 1,488 Hours
Estimated Labor Cost (Monthly) | $94,560

## 10.2 - Resources and Cost Plan (Bottom-Up Cost Plan)

The following tables will detail the Resource and Cost plan that utilizes the bottom-up cost estimation approach for the Smart Parking Platform. The costs are calculated and summed using bottom-up estimates for estimates for roles, labor, non-labor, tools, and additional resources that are relevant. There is also a 10% contingency that is applied to the base project cost to account for unexpected costs, scope changes, and similar things.

### 10.2.1 - Labor Costs

The HR Plan has 13 project resources with a combined estimated workload of 1,488 hours per month and total monthly labor cost of $94,560.

| Resource Category | Monthly Cost | Four-Month Cost (Monthly Cost × 4) |
| --- | --- | --- |
| Project Management, Product Ownership, Scrum Master | $13,000 | $52,000 |
| Technical Leadership | $9,000 | $36,000 |
| Development Teams | $48,480 | $193,920 |
| QA and Testing | $11,200 | $44,800 |
| SecOps | $5,600 | $22,400 |
| DevOps / CI/CD | $4,480 | $17,920 |
| UI/UX | $2,800 | $11,200 |
| Total Labor Cost | $94,560 | $378,240 |

### 10.2.2 - Non-Labor Costs

These are the non-labor costs that are associated with this project.

| Resource Category | Monthly Estimate | Four-Month Cost (Monthly Cost × 4) |
| --- | --- | --- |
| Cloud Hosting and Database | $2,000 | $8,000 |
| Mapping and Location APIs | $1,500 | $6,000 |
| Payment Integration and Testing | $1,300 | $5,200 |
| Software & Development Tools | $2,000 | $8,000 |
| SecOps and Privacy Compliance | $1,300 | $5,200 |
| Legal & Regulatory Compliance | $1,350 | $5,400 |
| Employee Training | $502 | $2,008 |
| Total Non-Labor Cost | $9,952 | $39,808 |

### 10.2.3 - Base Project Cost

The base project cost includes the costs of labor and non-labor expenses before contingency.

| Cost Component | Four-Month Cost |
| --- | --- |
| Labor | $378,240 |
| Non-Labor | $39,808 |
| Base Project Cost | $418,048 |

### 10.2.4 - Contingency

There will be a 10% contingency applied to the base project to account for unexpected costs, scope changes, and similar things.

$418,048 × 10% = $41,804.80

Contingency = $41,804.80

### 10.2.5 - Total Estimated Project Cost

| Cost Component | Four-Month Cost |
| --- | --- |
| Labor | $378,240 |
| Non-Labor | $39,808 |
| Base Project Cost | $418,048 |
| Contingency (10%) | $41,804.80 |
| Total Project Cost | $459,852.80 |

## 10.3 - High Level Cost Plan

This table shows the high-level bottom-up cost plan for the project.

| Item Category | Cost Type | Qty/Months | Unit Cost | Duration (Months) | Total |
| --- | --- | --- | --- | --- | --- |
| Project Labor | Labor | 5,952 Hours | $63.55/hr (AVG) | 4 | $378,240 |
| Cloud Hosting and Database | Infrastructure | $2,000/month | $2,000 | 4 | $8,000 |
| Mapping and Location Services | APIs | $1,500/month | $1,500 | 4 | $6,000 |
| Payment Integration and Testing | Integration | $1,300/month | $1,300 | 4 | $5,200 |
| Software and Development Tools | Tools | $2,000/month | $2,000 | 4 | $8,000 |
| SecOps and Privacy Compliance | Compliance | $1,300/month | $1,300 | 4 | $5,200 |
| Legal and Regulatory Compliance | Compliance | $1,350/month | $1,350 | 4 | $5,400 |
| Employee Training | Training | One-Time | $2,008 | Base | $2,008 |
| Contingency (10%) | Reserve | 10% | Applied to Base Cost | Not Applicable | $41,804.80 |
| Total Project Cost | $459,852.80 |  |  |  |  |

## 10.4 - Monthly Cashflows

This table shows the project monthly expenditures across the 4-month project. It includes labor costs, non-labor costs, and contingency reserves.

| Month/Phase | Labor | Non-Labor | Base Cost | Contingency (10%) | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 - Planning and Design | $78,315 | $11,458 | $89,773 | $8,977.30 | $98,750.30 |
| Month 2 - Development | $95,097 | $9,450 | $104,547 | $10,454.70 | $115,001.70 |
| Month 3 - Integration and Testing | $106,285 | $9,450 | $115,735 | $11,573.50 | $127,308.50 |
| Month 4 -SecOps, QA, and Deployment | $98,543 | $9,450 | $107,993 | $10,799.30 | $118,792.30 |
| Total | $378,240 | $39,808 | $418,048 | $41,804.80 | $459,852.80 |

Note: The contingency reserve is divided into 4 parts in the table, however, it can change based on its actual need. It is not fixed to the number in the table, but instead these are just estimates based on the phase of the project. In theory, the entire contingency dollar amount ($37,208) is going to sit in the reserve.

## 10.5 - RACI Matrix

This table will display the RACI Matrix for the Smart Parking Platform Project. 
R = Responsible, A = Accountable, C = Consulted, I = Informed

| Project Task | Project Manager | Product Owner | Scrum Master | Tech Lead | Dev Teams | QA | SecOps | Stakeholders | DevOps / CI/CD | UI/UX |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering and Scope | A | R | C | C | C | C | C | C | I | C |
| Product Backlog | C | A/R | C | C | C | I | C | C | C | C |
| System Architecture and Technical Design | I | C | C | A/R | C | C | C | I | C | C |
| Application and Backend Development | I | C | C | A | R | C | I | I | C | C |
| Platform Services and Data Integration | I | C | C | A | R | C | C | I | C | R |
| SecOps, Privacy, and Compliance | C | C | C | A | C | C | R | C | C | R |
| System Integration and Performance | I | C | C | A | R | R | C | I | R | R |
| Functional and Quality Testing | I | C | C | C | R | A/R | R | I | R | C |
| System Validation and Stakeholder Feedback | A | R | C | C | R | R | C | C | C | C |
| Project Approval and Usage | R | C | C | C | I | C | C | A/R | C | C |

## 10.6 - Resource and Cost Management Assumptions

1. The project uses a 4-month budgeting period for monthly cashflow planning

2. Full-time employee allocation is estimated at 160 hours per month.

3. The project uses a bottom-up cost estimation method.

4. Clod, mapping, payment, and development-tool costs are estimated monthly.

5. A 10% contingency is applied to the total base project.

6. The company’s unlimited theoretical budget does not mean there isn’t a need to monitor project costs.

7. The actual spending numbers and statistics would be compared against the cost baseline as the project makes progress.

# 11. Stakeholder Analysis

This section goes over the Stakeholder Analysis which details which parties are affected and are a part of the Smart Parking Platform Project.

## 11.1 - Power Interest Grid

This power interest grid maps each stakeholder to the appropriate quadrant regarding their power and interest in the project.

Upper Right = High Power, High Interest, Manage Closely
Lower Right = High Power, Low Interest, Keep Informed
Upper Left = Low Power, High Interest, Keep Satisfied
Lower Left = Low Power, Low Interest, Monitor

# 12. Team Charter

This charter goes over the team working on the project to define its purpose, goals, roles, and how they are going to operate when working on this project.

\

## 12.1 - Team Information

| Field | Details |
| --- | --- |
| Team Name | WE ARE $oftware ¢orp |
| Course | CIS 4374 |
| Project | Smart Parking Platform Project |
| Version | 4.0 |
| Date | October 2026 |

## 12.2 - Team Scope

Within Team Scope:
- Plan, design, develop, and test the web and mobile platform
- Implement parking querying, availability, maps, reservations, payments, and notifications
- Develop operator dashboards, occupancy monitoring, and reporting
- Integrate external mapping and payment services
- Validate usability, SecOps, and performance

Outside Team Scope:
- Physical installation of parking sensors or hardware
- Construction or modification of parking facilities
- Development of external payment or mapping services themselves

## 12.3 - Team Goals

Team Goals:

- Completing project deliverables within the four-month semester schedule

- Meeting approved functional and non-functional requirements

- Delivering usable interfaces for every type of user

- Completing integration and testing within the semester schedule

- Maintain accurate documentation and project progress

## 12.4 - Team Strengths/Skills

The team combines project management, software architecting, web and mobile development, backend/API development, UI/UX design, 3rd party mapping and payment services integration, quality assurance, SecOps, and DevOps. These strengths support the development and validation of the Smart Parking Platform.

## 12.5 - Roles and Responsibilities

| Role / Team | Primary Responsibilities |
| --- | --- |
| Project Manager | Schedule, budget, risk management, stakeholder communication, and project coordination. |
| Product Owner | Product requirements, backlog importance ranking, and stakeholder needs. |
| Scrum Master | Scrum events, team coordination, blockers, process improvement. |
| Technical Lead / Lead Architect | Architecture, technical decisions, and cross-team technical collaboration and dependencies. |
| Mobile Application Team | Mobile application development |
| Web Application Team | Web application development |
| Backend/API Team | Backend services, API integration, database, authentication, and business logic. |
| Mapping / Services Team | Mapping, geolocation, parking locations, navigation functionality. |
| Payment Integration Team | Payment processing and payment service integration. |
| QA and Testing Team | Functionality, integration, performance, reliability, and system testing. |
| SecOps Specialist | Authentication, authorization, privacy, confidentiality, SecOps testing. |
| DevOps / CI/CD Team | Build pipelines, automated checks, and deployment support. |
| UI/UX Team | Wireframes, prototypes, user interfaces, accessibility, and usability |

## 12.6 - Success Metrics

Success Metrics:

- Approved requirements are implemented and approved

- Core workflows get past acceptance tests

- All functional and non-functional requirements are met and satisfied

- Integrations work in testing environments

- Testing, validation, and project documentation is completed during the project schedule

## 12.7 - Values and Norms

Values

Accountability  Take responsibility for assigned work and due dates
Collaboration  Share knowledge and help resolve team blockers
Respect  Consider feedback and communicate professionally
Honesty  Report progress, risks, delays, and updates honestly
Quality  Put an importance on testing, usability, and reliable results

Norms

- Update Jira tasks and report blockers

- Provide daily asynchronous updates (Completed Work, Planned Work, Blockers, etc.)

- Attend weekly progress meetings and scheduled instructor check-ins

- Review work against acceptance criteria before making it complete

- Discuss things respectfully and escalate issues to the appropriate role

- Review team processes during sprint retrospectives

## 12.8 - Communication Plan and Coordination Tools

Jira  Product Backlog, sprint planning, assignments, important, and task status
Slack/Discord  Daily asynchronous updates and quick team communication
Microsoft Teams  Weekly meetings, progress reviews, and collab discussions
Project Repository  Store project documentation, designs, decisions, and deliverables
Instructor Check In  Review project progress and address course concerns
Sprint Retrospectives  Identify Improvements at the conclusion of each sprint
Stakeholder Check-In  Project Manager updates stakeholders on project progress and updates

## 12.9 - Extra Team Details

FUN!

- Celebrate completed milestones and successful sprint goals

- Recognize individual contributions and team accomplishments

- Encourage team participation

Team Commitment

The team agrees to work collaboratively, communicate appropriately, take ownership of responsibilities and deliver the Smart Parking Platform according to the approved requirements, project standards, and the semester schedule.

# 13. Project Charter

The project charter formally authorizes the existence of the Smart Parking Platform project and provides the Project Manager (Mitch Carter) with the authority to apply and use organizational resources to run project activities and processes. It highlights the project’s purpose, objectives, scope, and direction.

## 13.1 - Project Information

| Field | Details |
| --- | --- |
| Project Title | Smart Parking Platform |
| Sponsor / Client | City Transportation Department |
| Performing Org or Studio | WE ARE $oftware ¢orp |
| Course | CIS 4374 |
| Project Manager | Mitch Carter |
| Estimated Start Date | Month 1 (Academic Semester) |
| Estimated Conclusion Date | Month 4 (4-Month Timeline) |
| Approved Budget | $459,852.80 (Includes 10% Contingency) |
| Version | 4.0 |
| Date | October 2026 |

## 13.2 - Project Purpose and Business Need

WE ARE $oftware ¢orp was approached by a City Transportation Department client to plan, design, construct, and deliver a web and mobile platform that can provide real-time parking availability, reservations, payments, navigation, and management tools. This is due to drivers spending significant time querying regarding available parking which leads to frustration and congestion. Parking operators need better tools to monitor occupancy, manage pricing, and improve parking asset utilization. The application should help drivers locate, reserve, and pay for parking spaces for parking garages in real time. The project must follow compliance and regulatory rules that are set in place regarding parking. The is the reason why this project has been put into motion.

## 13.3 - Project Objectives

Project Objectives

- Develop a web and mobile platform for drivers and parking operators

- Provide parking querying, availability information, interactive maps, and facility details

- Support parking reservations, modifications, stopping reservations, digital payments, and receipts

- Provide operator tools for facility management, monitoring, and reporting

- Integrate external mapping and payment services

- Meet agreed requirements and compliance standards within the approved schedule and budget

## 13.4 - Project Scope

### 13.4.1 - Project In-Scope

- User Registration and Authentication

- Parking Querying and Real-Time Availability

- Interactive Parking Map

- Parking Facility Information

- Parking Reservations

- Digital Payment Processing

- Reservation History and Receipts

- Notifications

- Operator Dashboard

- Reporting and Analytics

- Integration of External Systems

- System Integration and Testing

- Web and Mobile Applications

- Access Controls

- CI/CD Pipelines and Automated Testing

- Deployment Support

### 13.4.2 - Project Out-Of-Scope

- Parking Infrastructure

- Deployment of Parking Sensors

- Hardware Deployment

- Parking Enforcement

- Management of Parking Facilities

- Proprietary Mapping or Payment Networks

- Ownership of Parking Facilities

## 13.5 - Key Deliverables

| Number | Deliverable | Description |
| --- | --- | --- |
| 1 | Requirements and Scope Documentation | Project Vision, Scope Definition, SRS, Functional and Non-Functional Requirements |
| 2 | Stakeholder Analysis | Power–Interest Grid, stakeholder register, and stakeholder engagement strategies. |
| 3 | Project and Team Charters | Project objectives, scope, authority, team structure, responsibilities, and working agreements. |
| 4 | Project Scheduling and Agile Planning | Work Breakdown Structure (WBS), Gantt chart, product backlog, and Scrum sprint board. |
| 5 | Risk and Communication Management | Risk register, mitigation strategies, communication schedule, and escalation procedures. |
| 6 | Resource and Cost Management Plan | Resource allocation, RACI matrix, bottom-up cost estimates, contingency reserve, and cashflow projections. |
| 7 | Platform Prototype | Web and mobile platform components supporting parking search, availability, reservations, payments, and operator functions. |
| 8 | Quality Assurance and testing Documentation | Test plans, test results, and validation of functional and non-functional requirements. |
| 9 | Deployment and Project Handoff Package | Final application deliverables, deployment documentation, technical documentation, and project handoff materials for it. |

## 13.6 - Project Milestones

| Month | Project Phase | Key Milestone and Completion Criteria |
| --- | --- | --- |
| Month 1 | Planning and Design | Complete project requirements, SRS, stakeholder analysis, project and team charters, WBS, initial product backlog, and UI/UX wireframes. |
| Month 2 | Core Development | Complete user registration and authentication, parking search, availability displays, interactive maps, and initial reservation functionality. |
| Month 3 | Integration | Complete reservation and payment workflows, mapping and payment integrations, operator dashboard, occupancy monitoring, and reporting features. |
| Month 4 | Testing and Deployment | Complete functional, integration, performance, and more testing. Finalize documentation and prepare the deployment and handoff package. |

## 13.7 - Budget Summary

| Cost Component | Four-Month Cost |
| --- | --- |
| Labor | $378,240 |
| Non-Labor | $39,808 |
| Base Project Cost | $418,048 |
| Contingency (10%) | $41,804.80 |
| Total Project Cost | $459,852.80 |

Note: Refer to Section 10.2 through Section 10.6 more detailed information about the budget and estimations that were made regarding it.

## 13.8 - Key Stakeholders

- Project instructor and academic evaluator.

- Project Manager and Product Owner.

- Development, QA, UI/UX, SecOps, and DevOps teams.

- Drivers and other parking users.

- Parking operators and facility staff.

- Project sponsor or funder, if applicable.

- External mapping and payment service providers.

- Relevant security, privacy, and regulatory authorities.

## 13.9 - Key Assumptions, Limitations, and Risks

Assumptions and Limitations:

- The project will be completed within the planned semester schedule.

- Third-party mapping and payment services will be available for integration and testing.

- Required development tools and test environments will be accessible.

- Physical parking hardware is not part of the project.

- Security, privacy, applicable regulations, and city ordinances must be considered.

- Scope changes may affect schedule, cost, and available team capacity.

Risks:

- Delayed or inaccurate parking occupancy information.

- Mapping or payment provider outages and integration difficulties.

- Security vulnerabilities or privacy compliance issues.

- Schedule delays caused by incomplete requirements or late design handoffs.

- Insufficient time for integration, testing, and deployment preparation.

- Cost increases or unapproved scope changes.

## 13.10 - Success Criteria (High Level)

- Approved requirements are implemented and validated.

- Core driver and operator workflows pass agreed acceptance tests.

- External service integrations operate as intended in the test environment.

- Security, privacy, performance, and usability requirements are evaluated.

- Project deliverables are submitted within the approved schedule and budget, or deviations are documented and approved.

## 13.11 - Project Authorization for Smart Parking Platform Project

The project charter establishes the project's purpose, scope, objectives, estimated cost, schedule, and responsibilities. Formal authorization should be recorded by the designated sponsor or instructor, as appropriate for the course project. Entries will be updated accordingly when parties want to sign.

| Approval Role | Name/Signature | Date |
| --- | --- | --- |
| Project Manager | Mitch Carter | October 28th, 2026 |